## Sheet1
Project Idea Management System - PIMS MOM (09-09-2021)
S.No | Module | description | Date | Status | Remarks
1 | Main dashboard | Total suggesion count exeeds value of 1000 , it adds the value from the count of 0 | 2021-09-09 | bug fixed | Meet to check and verified
|  | By selecting any two checkbox in category field , it list out all the checkbox value in employee list Table | 2021-09-09 | bug fixed | Meet to check and verified
|  | employee table in status column condition mismatching(Report Vs Reality) | 2021-09-09 | bug fixed | Meet to check and verified
2 | DBM Dashboard | display the graph value count mismatching checking inbox value of 0 | 2021-09-09 | bug fixed | Meet to check and verified
3 | CommitteeLogin | Automatically idea Id not displayed the popup | 2021-09-09 | bug fixed | Meet to check and verified
|  | Reject and Accept all need to be redirect/ always shows the reject id in accept inbox | 2021-09-09 | bug fixed | Meet to check and verified
4 | Manager Login/ DBM Login | manager cannot able to access of new employee add , edit and delete | 2021-09-09 | Open | Meet to check and verified
5 | production,manifactureEngineering | List of Suggestion need be differentciante in different division | 2021-09-09 | bug fixed | Meet to check and verified
|  |  | 2021-09-09 | bug fixed | Meet to check and verified
7 | Id pi-248 Vengadesan Login | While forwarding the suggesstion the comments message shows only manager comment not others Like n-1,n-2,n-3 | 2021-09-09 | Open | Meet to check and verified
8 | Id pi-215 Manager Login | Not able to create the new Option for manager to change in Role | 2021-09-09 | Open | Meet to check and verified