## Sheet1
1. Employee suggestion screen – Supervisor/Team leader drop down list. | DONE | VIGNESH
2. Suggestion view in HR screen. | BENDING
3. Implementer & Idea creator details to be available in finance report. | BENDING | VIGNESH
4. Implementer & Idea owner % change as discussed. | DONE | VIGNESH
5. Name Font standardization in all screens. |  | JAYA
6. Idea Id to be initiated from 001 and all test suggestions to be removed while going for live. |  | JAYA
7. In HR screen, Kindly modify labels as Accepted Ideas (User), Implemented Ideas (Implement). |  | JAYA
8. Ensure label names in all charts properly ( For Eg, super as supervisor, EMPDBM as Employee) |  | JAYA
9. Attached image for login screen background. |  | JAYA