## September
BINARY2QUANTUM TECHBASE (Daily Activity Sheet)
SNO | DATE | PROJECT | MODULE | TASK ASSIGNED | ACTIVITIES | STATUS | PROJECT LEVEL | REPORTING TO | TIME ESTIMATED | TIME TAKEN | COMMENTS | RISK
1 | 16.09.21 |  |  |  | Install the visual studio(not installed) and sql server(done) |  |  | Ms Dhanasagary | 1 Day | 10.05 - 7.30 | __
|  | ____ |  | Ms Dhanasagary |  | Done
2 | 17.09.21 | ____ |  | Ms Dhanasagary | learn the sql quarries(unions) try to install the visual studio(not done) |  |  | Ms Dhanasagary | 1 Day | 10.05 - 7.30 | __
Done
3 | 18.09.21 |  |  |  | Learn basic in bootstrap ( intro, containers,typography,contextual text and colors ,modal,popover)-done |  |  | Ms Dhanasagary | 1 Day | 10.15 - 7.25 | Learn basic in bootstrap ( intro, containers,typography,contextual text and colors ,modal,popover)-done
|  | PIMS |  | Ms Dhanasagary |  | Done
4 | 20.09.21 | PIMS | Bootstrap Topics | Ms Dhanasagary | Topics(jumbotron,wells,alerts,buttons,buttons group) | Done |  | Ms Dhanasagary | 1 Day | 10.30 - 7.00 | Topics(jumbotron,wells,alerts,buttons,buttons group)
5 | 21.09,21 |  |  |  | 1. Learn Basic of Java scripts(Functions, arrays, declarations , variables , syntaxs) 2 . Task given by TL in java scripts |  |  | Ms Dhanasagary | 1 Day | 10.00-8.00 | 1. Learn Basic of Java scripts(Functions, arrays, declarations , variables , syntaxs) 2 . Task given by TL in java scripts
|  | PIMS | Java scripts | Ms Dhanasagary |  | 1. In progress 2. in progress
6 | 22.09.21 | PIMS | Java scripts(jquerry and ajax) | Ms Dhanasagary | 1. Task given by TL in java scripts -- Done 2. Task given by TL in jquerry and ajax -- In process | 1. Done 2.In process |  | Ms Dhanasagary | 1 Day | 9.45-8.00 | 1. Task given by TL in java scripts -- Done 2. Task given by TL in jquerry and ajax -- In process
7 | 23.09.21 | PIMS | Java scripts(jquerry and ajax) | Ms Dhanasagary | 1. Task given by TL in jquerry and ajax -- Done 2. sql installation is finished --done | 1-- Done 2-- Done |  | Ms Dhanasagary |  | 9.45-7.50 | 1. Task given by TL in jquerry and ajax -- Done 2. sql installation is finished --done
8 | 24.09.21 | PIMS | __ | Ms Dhanasagary | visual studio installation process and PIMS project "KT" and "UPDATED SOURCE CODE " get from jayalakshmi .... | Done |  | Ms Dhanasagary |  | 10.45-7.30 | visual studio installation process and PIMS project "KT" and "UPDATED SOURCE CODE " get from jayalakshmi ....
9 | 28.09.21 | PIMS | __ | __ | Analyzing the PIMS project flow and then attend the PIMS project client meeting finally get some help from senior developer(Mr.Raja)---- | Done |  | ___ | 1Day | 9.40 -8.45 | Analyzing the PIMS project flow and then attend the PIMS project client meeting finally get some help from senior developer(Mr.Raja)---
10 | 29.09.21 | PIMS | __ | __ | 1. PIMS project analyzing from code side 2. Fixing the bugs | 1- In process 2- To do |  | Ms Dhanasagary | 1Day | 9.50-.7.40 | PIMS project analyzing from code side -in process , Fixing the bugs -to do
11 | 30.09.21 | PIMS | _ | Ms. Dhanasagary | 1. sql installation and visual studio instalation are install in the given laptop 2. plan to solve issues of pims project | 1. Done 2.Done |  | Ms Dhanasagary | 1 Day | 10.10-8.30 | 1. sql installation and visual studio instalation are install in the given laptop -- Done 2. plan to solve issues of pims project -Done

## october(2021)
BINARY2QUANTUM TECHBASE (Daily Activity Sheet)
SNO | DATE | PROJECT | MODULE | TASK ASSIGNED | ACTIVITIES | STATUS | PROJECT LEVEL | REPORTING TO | TIME ESTIMATED | TIME TAKEN | COMMENTS | RISK
1 | 01.10.21 |  |  |  | category flow check in the pims project - in process |  |  | Ms Dhanasagary | 1 Day | 09.50 - 7.30 | category flow check in the pims project - in process
|  | PIMS | CATEGORY | Ms Dhanasagary |  | In process
2 | 02.10.21 |  |  |  | 1.category flow check in the pims project - Done 2.suggestion status issues in Hod dashboard its also showing a correct status . Done |  |  | Ms Dhanasagary | 1 Day | 10.30 - 8.00 | 1. category issues fixed no changes its already correct in flow . Done 2. suggestion status issues in Hod dashboard its also showing a correct status . Done
|  | PIMS | CATEGORY | Ms Dhanasagary |  | Done
3 | 04.10.21 |  |  |  | 1. commitee and benificial to finance flow -- in process 2. The suggestion retrive process in manager and hod page -- Done 3. DBM dashboard Graph chart bar count identify and check excel count process( i have clarify some bars )-- in process |  |  | Ms Dhanasagary | 1 Day | 10.00 - 8.01 | 1. commitee and benificial to finance flow -- in process 2. The suggestion retrive process in manager and hod page -- Done 3. DBM dashboard Graph chart bar count identify and check excel count process( i have clarify some bars )-- in process
|  | PIMS | PIMS issuse | Ms Dhanasagary |  | in process
4 | 07.10.21 |  |  |  | Graph count Vs Real count is not same count in role based login while downloading the excel -Done graph chart full flow checked by the way of UI,DB,and code- Done |  |  | Ms Dhanasagary | 1 Day | 09.40 - 7.30 | Graph count Vs Real count is not same count in role based login while downloading the excel -Done graph chart full flow checked by the way of UI,DB,and code- Done
|  | PIMS | PIMS issuse | Ms Dhanasagary |  | Done
5 | 08.10.21 |  |  |  | 1. Pims project publish and remote access both kt get from jayalakshimi 2. pims project modification kt also give by jayalakshmi |  |  | Ms Dhanasagary | 1 Day | 09.40 - 8.00 | 1. Pims project publish and remote access both kt get from jayalakshimi 2. pims project modification kt also give by jayalakshmi
|  | PIMS | PIMS KT | Ms Dhanasagary |  | Done
6 | 09.10.21 |  |  |  | Task given by jayalakshmi to identify the hod button to visible in the role based login page - In process |  |  | Ms Dhanasagary | 1 Day | 09.40 - 8.10 | Task given by jayalakshmi to identify the hod button to visible in the role based login page - In process
|  | PIMS | PIMS Task | Ms Dhanasagary |  | In process
7 | 11.10.21 |  |  |  | Task given by jayalakshmi to identify the hod button to visible in the role based login page |  |  | Ms Dhanasagary | 1 Day | 09.40 - 8.00 | Task given by jayalakshmi to identify the hod button to visible in the role based login page - DONE
|  | PIMS | PIMS Task | Ms Dhanasagary |  | DONE
8 | 12.10.21 |  |  |  | Analaysing the js_script used in the pims project-In process |  |  | Ms Dhanasagary | 1 Day | 09.40 - 8.01 | Analaysing the js_script used in the pims project-In process
|  | PIMS | PIMS Task | Ms Dhanasagary |  | In process
9 | 13.10.21 |  |  |  | popup creation in pims project - In process |  |  | Ms Dhanasagary | 1 Day | 10.20 - 7.20 | popup creation in pims project - In process
|  | PIMS | PIMS Task | Ms Dhanasagary |  | In process
10 | 15.10.21 |  |  |  | popup creation in pims project - In process |  |  | Ms Dhanasagary | 1 Day | 10.20 - 7.21 | popup creation in pims project - In process
|  | PIMS | PIMS Task | Ms Dhanasagary |  | In process
11 | 18.10.21 |  |  |  | popup creation in pims project |  |  | Ms Dhanasagary | 1 Day | 10.00 - 8.00 | popup creation in pims project - In process
|  | PIMS | PIMS Task | Ms Dhanasagary |  | In process
12 | 19.10.21 |  |  |  | 1.Pims project wrk flow demo presentation give to the Client 2 . Graph module as per client request to change the finance bar chart -Done 3. popup creation - In process |  |  | Ms Dhanasagary | 1 Day | 10.00 - 8.01 | 1.Pims project wrk flow demo presentation give to the Client 2 . Graph module as per client request to change the finance bar chart -Done 3. popup creation - In process
|  | PIMS | PIMS Task | Ms Dhanasagary |  | In process
13 | 20.10.21 |  |  |  | popup creation - In process |  |  | Ms Dhanasagary | 1 Day | 10.20 - 7.10 | popup creation - In process
|  | PIMS | PIMS Task | Ms Dhanasagary |  | In process
14 | 21.10.21 |  |  |  | 1.Using remote access for the client issues clarification, 2. As per client wants to show the new entry of suggestion count in the main aspx. page- Done 3. to identify the credential employees module where the idea details table values come and how to bind to that table- In process |  |  | Ms Dhanasagary | 1 Day | 10.05 - 7.15 | 1.Using remote access for the client issues clarification, 2. As per client wants to show the new entry of suggestion count in the main aspx. page- Done 3. to identify the credential employees module where the idea details table values come and how to bind to that table- In process
|  | PIMS | PIMS Task | Ms Dhanasagary |  | 2- Done 3-In process
15 | 22.10.21 |  |  |  | To identify the credential employees module where the idea details table values come and how to bind to that table- In process |  |  | Ms Dhanasagary | 1 Day | 10.40 - 7.30 | To identify the credential employees module where the idea details table values come and how to bind to that table- In process
|  | PIMS | PIMS Task | Ms Dhanasagary |  | In process
16 | 23.10.21 |  |  |  | In ` Idea details Tracking History table` accept count and reject count values are miss matching In the main aspx page accept and reject count in the credential employees Module- |  |  | Ms Dhanasagary | 1 Day | 9.50 - 7.40 | In ` Idea details Tracking History table` accept count and reject count values are miss matching In the main aspx page accept and reject count in the credential employees Module- In process
|  | PIMS | PIMS Task | Ms Dhanasagary |  | In process
17 | 25.10.21 |  |  |  | In ` Idea details Tracking History table` accept count and reject count values are miss matching In the main aspx page accept and reject count in the credential employees Module- |  |  | Ms Dhanasagary | 1 Day | 9.45 - 8.20 | In ` Idea details Tracking History table` accept count and reject count values are miss matching In the main aspx page accept and reject count in the credential employees Module- In process
|  | PIMS | PIMS Task | Ms Dhanasagary |  | In process
18 | 26.10.21 |  |  |  | 1. In ` Idea details Tracking History table` accept count and reject count values are miss matching In the main aspx page accept and reject count in the credential employees Module- Done 2. popup creation for user interaction in all Pims project aspx_pages - Done |  |  | Ms Dhanasagary | 1 Day | 9.50 - 7.35 | 1. In ` Idea details Tracking History table` accept count and reject count values are miss matching In the main aspx page accept and reject count in the credential employees Module- Done 2. popup creation for user interaction in all Pims project aspx_pages - Done
|  | PIMS | PIMS Task | Ms Dhanasagary |  | 1 - Done 2- Done
19 | 27.10.21 |  |  |  | 1. In main aspx page sparkline graph is not showing 2. program push to the git up account for the first time with the guide line of PL-Dhanasagary |  |  | Ms Dhanasagary | 1 Day | 9.45 - 7.45 | 1. In main aspx page sparkline graph is not showing - Done 2. program push to the git up account for the first time with the guide line of PL-Dhanasagary - Done
|  | PIMS | PIMS Task | Ms Dhanasagary |  | 1 - Done 2- Done
20 | 28.10.21 |  |  |  | In new employee adding process to create a employee's auto details creating in the credential employee module- In process |  |  | Ms Dhanasagary | 1 Day | 9.45 - 7.30 | In new employee adding process to create a employee's auto details creating in the credential employee module- In process
|  | PIMS | PIMS Task | Ms Dhanasagary |  | In process
21 | 29.10.21 |  |  |  | In new employee adding process to create a employee details auto selection in the credential employee module . i am facing a small struggle to show the auto generate department details - In process 2. updating the client server sql sp_procedure |  |  | Ms Dhanasagary | 1 Day | 9.40 - 8.00 | In new employee adding process to create a employee details auto selection in the credential employee module . i am facing a small struggle to show the auto generate department details - In process 2. updating the client server sql sp_procedure
|  | PIMS | PIMS Task | Ms Dhanasagary |  | In process

## November(2021)
BINARY2QUANTUM TECHBASE (Daily Activity Sheet)
SNO | DATE | PROJECT | MODULE | TASK ASSIGNED | ACTIVITIES | STATUS | PROJECT LEVEL | REPORTING TO | TIME ESTIMATED | TIME TAKEN | COMMENTS | RISK
1 | 02.11.22 |  |  |  | 1. As per client doubt manager send to the other department where the suggestion go . In the manager send popup there getting a number of email id's but the employee id only showing one so iam change the code to show the selected employe id and auto select the selected employee's id mail - Done 2. check the attachement error in the client server |  |  | Ms Dhanasagary | 1 Day | 10.10 - 8.30 | 1. As per client doubt manager send to the other department where the suggestion go . In the manager send popup there getting a number of email id's but the employee id only showing one so iam change the code to show the selected employe id and auto select the selected employee's id mail - Done 2. check the attachement error in the client server
|  | PIMS | PIMS Task | Ms Dhanasagary |  | 1- Done
2 | 03.11.21 |  |  |  | c# face analyses project checking the work flow but we must fixing the sql port important !! |  |  | Ms Dhanasagary | 1 Day | 10.10 - 8.31 | c# face analyses project checking the work flow but we must fixing the sql port important !!
|  | PIMS | PIMS Task | Ms Dhanasagary |  | 1- Inprocess
3 | 06.11.22 |  |  |  | Employee auto generation details in the credential module department and designation values are getting some struggle to display |  |  | Ms Dhanasagary | 1 Day | 10.10 - 8.15 | Employee auto generation details in the credential module department and designation values are getting some struggle to display -in process
|  | PIMS | PIMS Task | Ms Dhanasagary |  | 1- Inprocess
4 | 15.11.21 |  |  |  | In employee add module department has a disable event creation as per client request - In process |  |  | Ms Dhanasagary | 1 Day | 09.50 - 7.30 | In employee add module department has a disable event creation as per client request - In process
|  | PIMS | PIMS Task | Ms Dhanasagary |  | 1- Inprocess
5 | 16.11.21 |  |  |  | In employee add module department has a disable event creation as per client request - In process |  |  | Ms Dhanasagary | 1 Day | 09.40 - 7.45 | In employee add module department has a disable event creation as per client request - In process
|  | PIMS | PIMS Task | Ms Dhanasagary |  | 1- Inprocess
6 | 17.11.21 |  |  |  | In employee add module department has a disable event creation as per client request - In process |  |  | Ms Dhanasagary | 1 Day | 09.40 - 8.30 | In employee add module department has a disable event creation as per client request - In process
|  | PIMS | PIMS Task | Ms Dhanasagary |  | 1- Inprocess
7 | 18.11.21 |  |  |  | In employee add module department has a disable event creation as per client request |  |  | Ms Dhanasagary | 1 Day | 11.30 - 7.15 | In employee add module department has a disable event creation as per client request - Done
|  | PIMS | PIMS Task | Ms Dhanasagary |  | 1- Done
8 | 20.11.21 |  |  |  | In all dashboard to show all comments in the Pims project-In process |  |  | Ms Dhanasagary | 1 Day | 10.00 - 7.35 | In all dashboard to show all comments in the Pims project-In process
|  | PIMS | PIMS Task | Ms Dhanasagary |  | 1- In process
9 | 24.11.21 |  |  |  | 1.In all dashboard to show all comments in the Pims project-In process 2. checking the magesh login id suggestion send to other department the drop down missing the two department managers in the client server -IN process |  |  | Ms Dhanasagary | 1 Day | 9.50 - 7.00 | 1.In all dashboard to show all comments in the Pims project-In process 2. checking the magesh login id suggestion send to other department the drop down missing the two department managers in the client server -IN process
|  | PIMS | PIMS Task | Ms Dhanasagary |  | In process
10 | 25.11.21 |  |  |  | 1.In all dashboard to show all comments in the Pims project-In process 2. checking the magesh login id suggestion send to other department the drop down missing the two department managers in the client server -Done |  |  | Ms Dhanasagary | 1 Day | 9.55 - 78.45 | 1.In all dashboard to show all comments in the Pims project-In process 2. checking the magesh login id suggestion send to other department the drop down missing the two department managers in the client server -Done
|  | PIMS | PIMS Task | Ms Dhanasagary |  | 1.In process 2.Done
11 | 26.11.21 |  |  |  | pims_shiftup documentation preparation for Database - IN process |  |  | Ms Dhanasagary | 1 Day | 10.30 - 8.00 | pims_shiftup documentation preparation for Database - IN process
|  | PIMS | PIMS Task | Ms Dhanasagary |  | In process

## December(2021)
BINARY2QUANTUM TECHBASE (Daily Activity Sheet)
SNO | DATE | PROJECT | MODULE | TASK ASSIGNED | ACTIVITIES | STATUS | PROJECT LEVEL | REPORTING TO | TIME ESTIMATED | TIME TAKEN | COMMENTS | RISK
1 | 03.12.21 |  |  |  | 1.In finance dashboard popup, div sections, inbox sections design are finished in the Pims_shiftup- Done 2. started to work in the backend process- IN process |  |  | Ms Dhanasagary | 1 Day | 09.30 - 8.10 | 1.In finance dashboard popup, div sections, inbox sections design are finished in the Pims_shiftup- Done 2. started to work in the backend process- IN process
|  | PIMS | PIMS Task | Ms Dhanasagary |  | 1- Done 2.In process
2 | 04.12.21 |  |  |  | manager idea suggestion details showing hover section -In Process |  |  | Ms Dhanasagary | 1 Day | 09.30 - 02.50 | manager idea suggestion details showing hover section -In Process
|  | PIMS | PIMS Task | Ms Dhanasagary |  | 1.In process
3 | 06.12.21 |  |  |  | manager idea suggestion details showing hover section |  |  | Ms Dhanasagary | 1 Day | 09.55 - 08.10 | manager idea suggestion details showing hover section -Done
|  | PIMS | PIMS Task | Ms Dhanasagary |  | 1.Done
4 | 07.12.21 |  |  |  | Inbox ,send ,assinged to own team,other team and from hr all mail send and recive and save to db process- In process |  |  | Ms Dhanasagary | 1 Day | 09.50 - 09.15 | Inbox ,send ,assinged to own team,other team and from hr all mail send and recive and save to db process- In process
|  | PIMS | PIMS Task | Ms Dhanasagary |  | 1.In process
5 | 08.12.21 |  |  |  | Inbox ,send ,assinged to own team,other team and from hr all mail send and recive and save to db process- In process |  |  | Ms Dhanasagary | 1 Day | 10.00 - 08.15. | Inbox ,send ,assinged to own team,other team and from hr all mail send and recive and save to db process- Done
|  | PIMS | PIMS Task | Ms Dhanasagary |  | 1.In process
6 | 09.12.21 |  |  |  | Code combine issuess -Fixed suggesstion flow checking-In process |  |  | Ms Dhanasagary | 1 Day | 10.00 - 10.45 | Code combine issuess -Fixed suggesstion flow checking-In process
|  | PIMS | PIMS Task | Ms Dhanasagary |  | 1.In process
7 | 10.12.21 |  |  |  | employee to manager suggestion send process -IN process |  |  | Ms Dhanasagary | 1 Day | 09.55 - 09.18 | employee to manager suggestion send process -IN process
|  | PIMS | PIMS Task | Ms Dhanasagary |  | 1.In process
8 | 11.12.21 |  |  |  | employee to manager suggestion send process -Done |  |  | Ms Dhanasagary | 1 Day | 09.55 - 07.15 | employee to manager suggestion send process - Done
|  | PIMS | PIMS Task | Ms Dhanasagary |  | 1.Done
9 | 13.12.21 |  |  |  | manager count ,suggesstion shownig and hod send process -Done |  |  | Ms Dhanasagary | 1 Day | 10.30 - 08.15 | manager count ,suggesstion shownig and hod send process -Done
|  | PIMS | PIMS Task | Ms Dhanasagary |  | 1.Done
10 | 16.12.21 |  |  |  | 1. IN hod login not feasible process- Done 2. In HR login not feasible , re-send ,pop up creation - In process 3. sql data base pims-shiftup created - In done |  |  | Ms Dhanasagary | 1 Day | 09.55 - 8.00 | 1. IN hod login not feasible process- Done 2. In HR login not feasible , re-send ,pop up creation - In process 3. sql data base pims-shiftup created - In done
|  | PIMS | PIMS Task | Ms Dhanasagary |  | 1.Done 2. In process
3.done
11 | 17.12.21 |  |  |  | In hr module popup ,not-feasible, re-send, creation - inprocess |  |  | Ms Dhanasagary | 1 Day | 09.05 - 8.00 | In hr module popup ,not-feasible, re-send, creation - inprocess
|  | PIMS | PIMS Task | Ms Dhanasagary |  | 1. In process
12 | 24.12.21 |  |  |  | In hr module re-send manager creation - DONE |  |  | Ms Dhanasagary | 1 Day | 09.30- 7.00 | In hr module re-send manager creation - Done
|  | PIMS | PIMS Task | Ms Dhanasagary |  | 1. Done
13 | 27.12.21 |  |  |  | 1.In all dashboard show the previous comment - in process 2. In Manager ,Hod,Hr,Main dashboard div counts and tabel count matching -In process 3. Testing issue on hod re-send tab count not showing -Done |  |  | Ms Dhanasagary | 1 Day | 11.15- 9.30 | 1.In all dashboard show the previous comment - in process 2. In Manager ,Hod,Hr,Main dashboard div counts and tabel count matching -In process 3. Testing issue on hod re-send tab count not showing -Done
|  | PIMS | PIMS Task | Ms Dhanasagary |  | 1.In process 2. In process 3.Done
14 | 28.12.21 |  |  |  | 1.In all dashboard show the previous comment except HOD Dashboard- in process 2.In hod dashboard show the previous comment - done 3. In Manager ,Hod,Hr,Main dashboard div counts and tabel count matching AS PER CLIENT NEW REQUIREMENT -In process |  |  | Ms Dhanasagary | 1 Day | 09.50- 7.50 | 1.In all dashboard show the previous comment except HOD Dashboard- in process 2.In hod dashboard show the previous comment - done 3. In Manager ,Hod,Hr,Main dashboard div counts and tabel count matching AS PER CLIENT NEW REQUIREMENT -In process
|  | PIMS | PIMS Task | Ms Dhanasagary |  | 1.In process 2. Done 3.Inprocess
15 | 29.12.21 |  |  |  | 1.IN hoddashboard resend tab countmismatch -Done 2. In Manager ,Hod,Hr,Main dashboard div counts and tabel count matching AS PER CLIENT NEW REQUIREMENT -In process |  |  | Ms Dhanasagary | 1 Day | 10.15- 10.30 | 1.In all dashboard show the previous comment 1.IN hoddashboard resend tab countmismatch -Done 2. In Manager ,Hod,Hr,Main dashboard div counts and tabel count matching AS PER CLIENT NEW REQUIREMENT -In process
|  | PIMS | PIMS Task | Ms Dhanasagary |  | 1. Done 2.In process
16 | 30.12.21 |  |  |  | 1. Hr dashboard count showing -Inprocess 2. In showing all comments Done bending incode combine to Jayalakshmi 's system - In process 3. Small errors fixing in manager dashboard -Done |  |  | Ms Dhanasagary | 1 Day | 09.45- 08.15 | 1. Hr dashboard count showing -Inprocess 2. In showing all comments Done bending incode combine to Jayalakshmi 's system - In process 3. Small errors fixing in manager dashboard -Done
|  | PIMS | PIMS Task | Ms Dhanasagary |  | 1-in[process 2.inprocess 3.done
17 | 31.12.21 |  |  |  | 1. after the Project publish small mis matchess in tab counts inthe manager and hod dashboard- done 2. In showing all comments Done bending incode combine to Jayalakshmi 's system - Done 3. Hr dashboard count showing -Done 4. In manager,hod,hr new modules to show the swal alert -Done 5. In employee task dashboard employe taskcomplete button click event the sender manager id auto get process suddenly not get the correct id - IN process |  |  | Ms Dhanasagary | 2 Day | 09.55- 07.35 | 1. after the Project publish small mis matchess in tab counts inthe manager and hod dashboard- done 2. In showing all comments Done bending incode combine to Jayalakshmi 's system - Done 3. Hr dashboard count showing -Done 4. In manager,hod,hr new modules to show the swal alert -Done 5. In employee task dashboard employe taskcomplete button click event the sender manager id auto get process suddenly not get the correct id - IN process
|  | PIMS | PIMS Task | Ms Dhanasagary |  | 1-Done 2.Done 3.done 4.done 5Inprocess

## JAN(2022)
BINARY2QUANTUM TECHBASE (Daily Activity Sheet)
SNO | DATE | PROJECT | MODULE | TASK ASSIGNED | ACTIVITIES | STATUS | PROJECT LEVEL | REPORTING TO | TIME ESTIMATED | TIME TAKEN | COMMENTS | RISK
1 | 03.01.22 |  |  |  | 1. To check the flow after the project deployment 2. in new suggestion page auto get manager id and mailid as per employes department head manager -Done 3. catogory as a multiselect dropdown in a new suggesstion page -Inprocess |  |  | Ms Dhanasagary | 1 Day | 10.15 - 8.10 | 1. To check the flow after the project deployment 2. in new suggestion page auto get manager id and mailid as per employes department head manager -Done 3. catogory as a multiselect dropdown in a new suggesstion page -Inprocessss
|  | PIMS | PIMS Task | Ms Dhanasagary |  | 2. Done 3.In process
2 | 05.01.22 |  |  |  | 1. In Manager and hod module to change the hover 's, adding the date in every nav tab , creating the tooltip and message indication -DONE 2. In Manager, hod, employee modules as per client wants to fitch the employee subject is to be show in every subject text box -DONE 3. In Idea tracking details tabel re-modified -In process |  |  | Ms Dhanasagary | 1 Day | 10.15 - 8.20 | 1. In Manager and hod module to change the hover 's, adding the date in every nav tab , creating the tooltip and message indication -DONE 2. In Manager, hod, employee modules as per client wants to fitch the employee subject is to be show in every subject text box -DONE 3. In Idea tracking details tabel re-modified -In process s
|  | PIMS | PIMS Task | Ms Dhanasagary |  | 1-DONE 2-DONE
3-In process
3 | 08.01.22 |  |  |  | 1.In Hod module employee and implementor both are separate score creation -In process 2. In hr module to create a approved button to push the suggestion as a separate idea suggestion to finance -In process |  |  | Ms Dhanasagary | 1 Day | 10.20 - 8.15 | 1.In Hod module employee and implementor both are separate score creation -In process 2. In hr module to create a approved button to push the suggestion as a separate idea suggestion to finance -In process
|  | PIMS | PIMS Task | Ms Dhanasagary |  | 1-In process 2-In process
4 | 10.01.22 |  |  |  | 1.In Hod module employee and implementor both are separate score creation 2. In hr module to create a approved button to push the suggestion as a separate idea suggestion to finance |  |  | Ms Dhanasagary | 1 Day | 10.20 - 8.25 | 1.In Hod module employee and implementor both are separate score creation 2. In hr module to create a approved button to push the suggestion as a separate idea suggestion to finance
|  | PIMS | PIMS Task | Ms Dhanasagary |  | 1-DONE 2-DONE
5 | 11.01.22 |  |  |  | In Finance Module user_employe and Imple_employe to insert a data Inbox and complete in mail repeater -Done |  |  | Ms Dhanasagary | 1Day | 09.50 - 7.10 | In Finance Module user_employe and Imple_employe to insert a data Inbox and complete in mail repeater -Done
|  | PIMS | PIMS Task | Ms Dhanasagary |  | 1-DONE
6 | 17.01.22 |  |  |  | 1. In new suggesstion page to get the supervisor id ,name and mail id using employee role department - done 2. In all response page textbox field to non editable by user- Done 3. In supervisor Page and manager page to modify the report as per current requirement - Done |  |  | Ms Dhanasagary | 1Day | 10.00 - 7.50 | 1. In new suggesstion page to get the supervisor id ,name and mail id using employee role department - done 2. In all response page textbox field to non editable by user- Done 3. In supervisor Page and manager page to modify the report as per current requirement - Done
|  | PIMS | PIMS Task | Ms Dhanasagary |  | 1-DONE 2-Done 3-done
7 | 18.01.22 |  |  |  | 1.In Supervisor module suggestion move to other deptartment - Done 2. code combine (done) and some errors on the hod resend process and manager resend process - In process |  |  | Ms Dhanasagary | 1Day | 09.35 - 09.45 | 1.In Supervisor module suggestion move to other deptartment - Done 2. code combine (done) and some errors on the hod resend process and manager resend process - In process
|  | PIMS | PIMS Task | Ms Dhanasagary |  | 1-DONE 2-In process
8 | 19.01.22 |  |  |  | 1.All module suggestion flow process- Done 2. To work on the latest wanted in manager and implement module- In process |  |  | Ms Dhanasagary | 1Day | 09.35 - 09.46 | 1.All module suggestion flow process- Done 2. To work on the latest wanted in manager and implement module- In process
|  | PIMS | PIMS Task | Ms Dhanasagary |  | 1-DONE 2-In process
9 | 20.01.22 |  |  |  | 1. In Employee task module Send count mismatching - Done 2. In Manager module resend to implement count- Done 3. Finance module user inbox not showing and implement download the excel details is not getting the values-Done |  |  | Ms Dhanasagary | 1Day | 09.35 - 08.00 | 1. In Employee task module Send count mismatching - Done 2. In Manager module resend to implement count- Done 3. Finance module user inbox not showing and implement download the excel details is not getting the values-Done
|  | PIMS | PIMS Task | Ms Dhanasagary |  | 1-DONE 2-Done 3-DONE
10 | 21.01.22 |  |  |  | 1. Yesterday finished modules to update in miss jayalakshmi 's system -Done 2. To go throw the email api and to create a sample mail in web form -In process |  |  | Ms Dhanasagary | 1Day | 09.25 - 09.48 | 1. Yesterday finished modules to update in miss jayalakshmi 's system -Done 2. To go throw the email api and to create a sample mail in web form -In process
|  | PIMS | PIMS Task | Ms Dhanasagary |  | 1-DONE 2-In process
11 | 22.01.22 |  |  |  | 1. In Md login the send button is not working in Supervisor,manager modulesissue-Done 2. In all Modules the idea id value removing the unwanted white space - Done 3. As per client requirement the new suggestion page the supervisor must be the dropdown list to specific employes derartment -Done 4. Testing How was the mail goes in poclain -In process |  |  | Ms Dhanasagary | 1Day | 09.45 - 08.30 | 1. In Md login the send button is not working in Supervisor,manager modulesissue-Done 2. In all Modules the idea id value removing the unwanted white space - Done 3. As per client requirement the new suggestion page the supervisor must be the dropdown list to specific employes derartment -Done 4. Testing How was the mail goes in poclain -In process
|  | PIMS | PIMS Task | Ms Dhanasagary |  | 1-DONE 2-DONE 3-DONE 4-IN PROCESS
12 | 31.01.22 |  |  |  | 1.In supervisor and manager dashboard department id wise suggesstion showing in mailrepeater -Done 2.In supervisor dashboard suggestion send to otherdepartment -In process |  |  | Ms Dhanasagary | 1Day | 12.15 - 08.31 | 1.In supervisor and manager dashboard department id wise suggesstion showing in mailrepeater -Done 2.In supervisor dashboard suggestion send to otherdepartment -In process
|  | PIMS | PIMS Task | Ms Dhanasagary |  | 1-DONE 2-In process

## FEB(2022)
BINARY2QUANTUM TECHBASE (Daily Activity Sheet)
SNO | DATE | PROJECT | MODULE | TASK ASSIGNED | ACTIVITIES | STATUS | PROJECT LEVEL | REPORTING TO | TIME ESTIMATED | TIME TAKEN | COMMENTS | RISK
1 | 01.02.22 |  |  |  | 1. In supervisor module suggesstion send to otherdepartment -Done 2. supervisor creation -Done 3.manager creation -In process |  |  | Ms Dhanasagary | 1 Day | 09.35 - 10.10 | 1. In supervisor module suggesstion send to otherdepartment -Done 2. supervisor creation -Done 3.manager creation -In process
|  | PIMS | PIMS Task | Ms Dhanasagary |  | 1-Done 2.Done 3.In process
2 | 02.02.22 |  |  |  | 1. Code combine -Done 2.manager creation -Done |  |  | Ms Dhanasagary | 1 Day | 10.25 - 08.30 | 1. Code combine -Done 2.manager creation -Done
|  | PIMS | PIMS Task | Ms Dhanasagary |  | 1-Done 2.Done
3 | 03.02.22 |  |  |  | 1.In manager module suggesstion are directly showing the HOD tab issue-Done 2. The graph resend count missing issue-Done 3.In employee task upload files which place to store in database -Done 4. In all modules side page navigation bar is hide but the page redirect to the href page by client click issue-Done |  |  | Ms Dhanasagary | 1 Day | 10.25 - 10.12 | 1.In manager module suggesstion are directly showing the HOD tab issue-Done 2. The graph resend count missing issue-Done 3.In employee task upload files which place to store in database -Done 4. In all modules side page navigation bar is hide but the page redirect to the href page by client click issue-Done
|  | PIMS | PIMS Task | Ms Dhanasagary |  | 1-Done 2.Done 3.Done 4. Done
4 | 04.02.22 |  |  |  | 1. Implemented Upload file view design in magager ,hod, hr modul |  |  | Ms Dhanasagary | 1 Day | 10.25 - 07.15 | 1. Implemented Upload file view design in magager ,hod, hr modul
|  | PIMS | PIMS Task | Ms Dhanasagary |  | 1-In process
5 | 05.02.22 |  |  |  | 1. Visual studio and sql installation process in think pad laptop -Done 2. Image open but not close in the mail view design - In process |  |  | Ms Dhanasagary | 1 Day | 09.25 - 07.15 | 1. Visual studio and sql installation process in think pad laptop -Done 2. Image open but not close in the mail view design - In process
|  | PIMS | PIMS Task | Ms Dhanasagary |  | 1- done 2-In process
6 | 07.02.22 |  |  |  | In PIMS_SHIFTUP Report modification as per client request - DONE |  |  | Ms Dhanasagary | 1 Day | 08.00 - 07.15 | In PIMS_SHIFTUP Report modification as per client request - DONE
|  | PIMS | PIMS Task | Ms Dhanasagary |  | 1- done
7 | 08.02.22 |  |  |  | 1.In Hod creation the department will be a text but it should be a dropdown _-done 2. To check the client server newly published code |  |  | Ms Dhanasagary | 1 Day | 10.15 - 09.45 | 1.In Hod creation the department will be a text but it should be a dropdown _-done 2. To check the client server newly published code
|  | PIMS | PIMS Task | Ms Dhanasagary |  | 1- done
8 | 09.02.22 |  |  |  | 1.In finance Dashboard unwanted alerts are not commented - DONE 2. In FinanceImpl Dashboard The payment popup tha implementor name showing with the dbspace so the process was not working correctly . To fine out the error and rework the database values -DONE 3.In Su[ervisor,Manager and Hod creation page Alter and delete process are not working -IN PROCESS |  |  | Ms Dhanasagary | 1 Day | 10.30 - 08.30 | 1.In finance Dashboard unwanted alerts are not commented - DONE 2. In FinanceImpl Dashboard The payment popup tha implementor name showing with the dbspace so the process was not working correctly . To fine out the error and rework the database values -DONE 3.In Su[ervisor,Manager and Hod creation page Alter and delete process are not working -IN PROCESS
|  | PIMS | PIMS Task | Ms Dhanasagary |  | 1- done 2-done 3-done 4-In process
9 | 14.02.22 |  |  |  | 1.In Pims shift back flow process like (hr-hod-manager-implementor) process - done 2. In poclain_OEE project over view and code analysis process -In process |  |  | Ms Dhanasagary | 1 Day | 10.15 - 07.15 | 1.In Pims shift back flow process like (hr-hod-manager-implementor) process - done 2. In poclain_OEE project over view and code analysis process -In process
|  | PIMS | PIMS Task | Ms Dhanasagary |  | 1- done 2-In process
10 | 15.02.22 |  |  |  | 1. In pimsshiftup project miss jaya find out some error it was employee task mail view is not showing particularyPI-074 employeeid issue -Done 2.In OEE code analyses process -In process |  |  | Ms Dhanasagary | 1 Day | 09.35 - 07.10 | 1. In pimsshiftup project miss jaya find out some error it was employee task mail view is not showing particularyPI-074 employeeid issue -Done 2.In OEE code analyses process -In process
|  | PIMS | PIMS Task | Ms Dhanasagary |  | 1- done 2-In process
11 | 16.02.22 |  |  |  | In poclain webform project system capture screenshot while automatic exexting process arecreated old version but the old version image capturing ddl is not currently working so we find out the error and adding subsitite for old capturing process . Now its working |  |  | Ms Dhanasagary | 1 Day | 09.35 - 07.20 | In poclain webform project system capture screenshot while automatic exexting process arecreated old version but the old version image capturing ddl is not currently working so we find out the error and adding subsitite for old capturing process . Now its working
|  | OEE | PIMS Task | Ms Dhanasagary |  | 1- done
12 | 18.02.22 |  |  |  | 1.In OEE application work in local but after the publish the image casting are not supported so i get help from Miss dhanasagary she solve the problem now the project was running good - Done 2. in PIMS_SHIFTUP client told some issues to find out the issues -Done |  |  | Ms Dhanasagary | 1 Day | 09.35 - 08.15 | 1.In OEE application work in local but after the publish the image casting are not supported so i get help from Miss dhanasagary she solve the problem now the project was running good - Done 2. in PIMS_SHIFTUP client told some issues to find out the issues -Done
|  | OEE | PIMS Task | Ms Dhanasagary |  | 1- done 2-Done